## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Brandon | 6700 | 0 | 6700 | 2700 | 0 | 2700 | 2500 | 0 | 2500 | 1500 | 0 | 1500
Josh | 3800 | 0 | 3800 | 0 | 0 | 0 | 2500 | 0 | 2500 | 1300 | 0 | 1300
Lucas | 3800 | 0 | 3800 | 0 | 0 | 0 | 2500 | 0 | 2500 | 1300 | 0 | 1300
Sheldon | 3800 | 0 | 3800 | 0 | 0 | 0 | 2500 | 0 | 2500 | 1300 | 0 | 1300
Connor | 5000 | 250 | 4750 | 1200 | 250 | 950 | 2500 | 0 | 2500 | 1300 | 0 | 1300
Jubal | 3800 | 0 | 3800 | 0 | 0 | 0 | 2500 | 0 | 2500 | 1300 | 0 | 1300
Total | 26900 | 250 | 26650 | 3900 | 250 | 3650 | 15000 | 0 | 15000 | 8000 | 0 | 8000

## Gantt
| predicted time(hrs) | time spent(hrs) | key |  | completed |  |  | this week |  |  | planned
Brandon |  |  | hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
gantt chart creation | 3 | 0
track health / progress | 5 | 0
user interface | 10 | 0
pickup items | 6 | 0
placeholder | 0 | 0
placeholder | 0 | 0
testing | 3 | 0
totals | 27 | 0
Josh
logo creation | 0 | 0
Model Animation | 0 | 0
object modeling | 0 | 0
placeholder | 0 | 0
placeholder | 0 | 0
placeholder | 0 | 0
placeholder | 0 | 0
testing | 0 | 0
totals | 0 | 0
Lucas
programming - AI | 0 | 0
Sound Implementation | 0 | 0
level design | 0 | 0
mini map | 0 | 0
placeholder | 0 | 0
testing | 0 | 0
totals | 0 | 0
Sheldon
menu design | 0 | 0
programming ship controls | 0 | 0
placeholder | 0 | 0
placeholder | 0 | 0
placeholder | 0 | 0
testing | 0 | 0
totals | 0 | 0
Connor
setup GIT Hub | 1 | 1.5
collision detection | 10 | 0
create unity project | 1 | 1
placeholder | 0 | 0
placeholder | 0 | 0
testing | 0 | 0
totals | 12 | 2.5
Jubal
coding standard creation | 0 | 0
level design (2) | 0 | 0
placeholder | 0 | 0
placeholder | 0 | 0
placeholder | 0 | 0
testing | 0 | 0
totals | 0 | 0
group totals (hrs) | 39 | 2.5
group totals ($) | 3900 | 250

## Meetings
| Date | Jan. 24 | Feb. 3 | DATE | DATE | DATE | DATE | DATE | DATE | DATE | DATE
| Purpose | First Meeting | RFP / Game Planning | Future Meeting | Future Meeting | Future Meeting | Future Meeting | Future Meeting | Future Meeting | Future Meeting | Future Meeting
| Hours | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brandon | 0 | ü | ü
Josh | 0 | ü | ü
Lucas | 0 | ü | ü
Sheldon | 0 |  | ü
Connor | 0 | ü | ü
Dan | 0 | ü | ü
Total | 0 | 7.5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Brandon | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Merge Gantt Charts | 2 | 0 | bar: 12 to 13
| Assemble SA Powerpoint | 2 | 0 | bar: 14 to 15
| Subtotal | 15 | 0
Josh | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0
| Subtotal | 13 | 0
Lucas | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0
| Subtotal | 13 | 0
Sheldon | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0
| Subtotal | 13 | 0
Connor | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0
| Subtotal | 13 | 0
Jubal | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0
| Subtotal | 13 | 0
| Total | 80 | 0
red is dependent on others